## Task list - Core library
# | Priority | Story | Description | Progress | Added | Completed on
1 | high | Add support for editing existing text in TextRange class | TextRange should support basic text editing feature to create/update or remove text from documents. | done | 2015-02-01 | 2015-02-09
2 | high | Add support for creating substring in TextRange class | TextRange should support to create substring feature in text documents. | done | 2015-02-01 | 2002-02-15
3 | normal | TextDocument should handle duplicated TextRanges | When we register or create a new TextRange then TextDocument should check its existence to avoid duplications. | done | 2015-02-06 | 2015-02-06
4 | low | Remove TextRange | TextDocument should support removing text ranges from list. TextDocument should have a TextDocument.RemoveTextRange method for this feature. | done | 2015-02-09 | 2015-03-14
5 | normal | Create a stub visitor for CSV language | There should be a stub visitor for testing CSV grammar. | done | 2015-02-09 | 2015-03-03
6 | high | Implement a CSV tree factory for reduce dependency | There should be a factory for creating CSV node and it should build syntax and semantic tree as well | done | 2015-02-14 | 2015-02-14
7 | normal | Implement semantic trees and nodes | There should be implemented semantic nodes and trees data structure beside nodes | to-do | 2015-02-14
8 | low | Reconsider SelectRelativeNodesOperand implementation | When algorithm finds a proper valid node it should not continue search in its children | to-do | 2015-02-15
9 | low | Implement an error handling logic to the whole application | There should be a Protect-like method for handling errors and every exception should be caught. | to-do | 2015-02-24
10 | normal | Support 2D text ranges | It should support 2D text ranges for rectangular selection of texts | to-do | 2015-03-03
11 | high | Add DI support to CsvCompiler class | CsvCompiler class doesn't support dependency injection. Its Parse method or constructor should be extended. Dependencies should be tree visitors | done | 2015-03-07 | 2015-03-07
12 | high | Merge master-refactoring branch to master | Basically refactoring has been finished so two branches can be merged into one | to-do | 2015-03-14
13 | high | Add grammar project to repository | CodeSharper grammar project should be attached to existing project | to-do | 2015-03-14
14 | normal | Implement CodeQuery language into project | CodeQuery language is ready, it is time to implement and migrate into the project | in-progress | 2015-03-14
15 | normal | [Selectors] Implement selector language beside command calls | A selector language factory should be implemented | to-do | 2015-03-14
16 | normal | [Selectors] Create a resolver class for building node operands, modifiers and selectors | There should be implemented a resolver class for creating node operands, modifiers and selectors | to-do | 2015-03-15